## Global timeline
Disciplines | Timeline | Theme | Item | Resp. | Scope of Service | Refer to:
All | January of event year | ADMINISTRATION | Officials Nomination | CEC | CEC will nominate the following team of officials: - Technical Delegate (TD) - Jury President - Head Judge - Head Setter - Assistant Setter | -
All | January of event year | ADMINISTRATION | Rules Publication | CEC | CEC to publish rules
All | By March 31 | WEBCAST | Staff Planning | CEC | CEC, along with webcast provider, to provide staff assignments per event | -
All | By March 31 | WEBCAST | Staff Planning | CEC | CEC, along with webcast provider, to nominate commentator resource | -
All | 6 months b.e | ADMINISTRATION | Insurance certificate | CEC | CEC will send Host Gym confirmation of CEC insurance
All | 6 months b.e | ADMINISTRATION | Insurance certificate | Host Gym | Host Gym will send CEC a copy of the insurance certificate for the Event
All | 6 months b.e | COORDINATION | Event preparation | CEC | CEC, through the TD, will contact with Host Gym and define work plan and timeline in accordance with CEC regulations
All | 6 months b.e | COORDINATION | All actors coordination | TD | TD will act as the single contact between Host Gym and all involved CEC Departments, Officials and providers (including Webcast or other crew) TD will advise Host Gym on compulsory information to provide to CEC and other parties. CEC will also give the Host Gym the different information required for publication and promotion such as the provisional Event Schedule | -
All | 6 months b.e | COORDINATION | Information publication | Host Gym | Host Gym will provide the following information: - Draft Information Sheet for Team for validation by the TD and publication on the CEC Website - Draft Field of Play design - Climbing wall design - Event Schedule (comprising ceremonies, presentations, final rounds and reception) | -
All | 4 months b.e | Sport | Holds list | Host Gym | Host Gym to send list of available holds to the Chief Route Setter, which must meet the minimum requirements in the hosting application.
All | 4 months b.e | COORDINATION | Event schedule | TD | TD will review with Host Gym events schedules and timelines to verify compliance with CEC regulations. TD will advise on best schedules for good sport presentation . Final validation from CEC of the infosheet | -
All | 3 months b.e | COORDINATION | Wall design | TD / CRS | TD will review with Host Gym the wall and structure design, to verify accordance with the CEC safety regulation. TD will advise on best design for good sport presentation. CRS will review wall design in order to prepare route setting. | -
All | 3 months b.e | COORDINATION | FOP | TD | TD will advise Host Gym on FOP design for good sport presentation
All | 3 months b.e | COORDINATION | FOP | Host Gym | Host Gym to send a FOP layout and venue layout to CEC
All | 3 months b.e | COORDINATION | FOP | CEC | CEC to validate the FOP and venue layout
All | 3 months b.e | MEDIA | Information on Broadcaster Agreement | Host Gym | Host Gym will inform the CEC of possible Broadcaster agreement (if applicable) Host Gym will inform on live broadcasting or on site TV production
All | 3 months b.e | COORDINATION | Communication / Branding design | Host Gym | Host Gym will provide the following items, which require prior approval by CEC: - Event Branding (at a minimum to include physical posters and related media posts) to be validated by CEC (must comply with Graphic Charter & FOP Design) - Event Communication Plan - Event Media Plan - Volunteer Uniforms (including design thereof) - Athlete Bibs (including design thereof)
All | 1 month b.e | COORDINATION | Field of Play and Branding finalization | Host Gym | Host Gym will transfer to the CEC the final Field of Play design including the branding material
All | 1 month b.e | WEBCAST | First coordination meeting for technical planning | Host Gym | Host Gym will communicate technical situation regarding Webcasting to CEC and Webcaster
All | 1 month b.e | MEDIA | Media plan | CEC | The CEC shall be responsible for National media plan and provide a National press review. The Host Gym is responsible for local communications and media plan in collaboration with the CEC. | -
All | 15 days b.e | COORDINATION | Second package of Communication / branding design | Host Gym | Host Gym will transfer to the CEC the following items : - Event sponsors logos - Event general / digital info
All | 1 week b.e | STAFFING | Facility and volunteer staffing | Host Gym | Host Gym will communicate with TD final volunteer and facility staffing, ensuring the appropriate amount required as approved by CEC.
All |  | STAFFING | Medical Staff | Host Gym | Host Gym will provide appropriate medical staff, as approved by CEC, for the Event
All |  | STAFFING | Health Staff | Host Gym | Host Gym may provide massage, physio and other sport/recovery specific personnel
All | 1 week b.e | WEBCAST | Last coordination meeting | Host Gym | Host Gym will communicate last development on technical situation regarding Webcasting to Webcast
All | 1 week b.e, during, up to 2 days a.e | MEDIA | Social Media | CEC/Host Gym | CEC and Host Gym will promote each event through its social media and website | -
All | 5 days b.e at the latest & 2 days a.e at the latest | MEDIA | Press releases | CEC | The CEC shall write and distribute Press Releases related to all events, and shall require the Host Gym to provide a minimum information pertaining to the event no less than 15 days before the commencement of the event. Specifically, the CEC shall issue a Press Release both before and after the event. | -
Lead and boulder | 5 days b.e. until last day of event | HR during event | Route setting | CEC/Host Gym | CEC nominated Route Setting Team to arrive and take care of all route setting. Host Gym will provide equipment, on time, in accordance with relevant regulation. Host Gym will ensure wall shall be clean of holds with pads and / or belaying point installed and secured, to allow climbing and testing of the routes. In case of outdoor event, the wall should be covered to protect from the rain. If any change in the timetable for the competition is made since the info sheet publication, the Host Gym shall provide the latest version to the chief route setter. | Route Setter Check list
All | 5 days b.e. | COORDINATION | Latest timetable | Host Gym | Host Gym will communicate the latest timetable to CEC. TD may amend it if necessary.
All | 2 days b.e. to end of event | HR during event | Operations | CEC/TD | TD to arrive in order to assist and advise the Host Gym in general operation and in particular: - FOP branding and logo placement in agreement with what was defined with CEC. - Ceremonies and protocols - Schedules - CEC Rules and regulations - Athletes and Athletes' entourage | -
Lead and boulder | 1 day b.e. to end of event | HR during event | Judging | CEC | CEC President of Jury and Judge to manage the result production and assist national judges. Host Gym will provide equipment, on time, in accordance with relevant regulation. | Event Facilities
Speed | 1 day b.e. to end of event | HR during event | Judging | CEC | CEC President of Jury to manage the result production and assist national judges. Host Gym will provide equipment, on time, in accordance with relevant regulation. | Event Facilities
Speed | 1 day b.e. | HR during event | Homologation | CEC | CEC TD may proceed with homologation of the speed wall in accordance with relevant regulations | Speed world record license rules**
All |  | COORDINATION | Competition Equipment | Host Gym | Host Gym will provide adequate anciallry supplies for purpose of competition including: brushes for use by competitors and volunteers (as applicable), chairs for competitors in staging areas; tape and signage for FOP (including for identification of competition problems); and other ancilary competition equipment as would be customary for a similar event
All |  | COORDINATION | Food/Beverages | Host Gym | Host gym to ensure food and drink is available for event volunteers
All | 1 day b.e. | COORDINATION | Sequence of ceremonies | Host Gym | Host Gym will provide to TD a precise sequence of the presentation and other ceremonies scheduled at key movement of the event
All | 1 day b.e. | WEBCAST | In event coordination meeting | CEC | The CEC officials and the Host Gym should attend together a coordination meeting, webcasting's topic will be object of discussion
All | during event | COOR | Live feed | Host Gym | Host Gym to provide access to TV live feed when it is available | during event
All | during event | IT | Handheld devices | CEC | CEC will provide 5 Tablets for Lead events and 10 for Boulder. | -
All | during event | IT | Cameras | Host Gym | Host Gym will provide cameras based on the CEC regulations. All still photographers and videographers to be supplied by Host Gym, to extent applicable. | -
All | during event | IT | Timing System | Host Gym | Host Gym will provide timing system based on the CEC regulations | -
All | during event | IT | Graphics | CEC | CEC will turn live result data into graphics. CEC will provide feed, Host Gym will be responsible to display it onto audience screens. Webcast will be responsible to embed it onto webcasting. | -
All | during event | IT | Export for TV | CEC | Webcast will ensure live result and graphics can be exported for broadcasting purpose. | -
Lead and boulder | during event | IT | Live result, Bouldering | CEC | CEC will ensure score collected from Tablets will be turned to live results for Qualification, Semi-Finals and Finals. | -
Lead and boulder | during event | IT | Live result, Lead | CEC | CEC will ensure score collected from Tablets will be turned to live results for Semi-Finals and Finals. | -
Speed | during event | IT | Live result, Speed | CEC | CEC Officials will ensure time collected from Speed Timing Systems will be turned to live results. | -
All |  | COORDINATION | Prizes | CEC | CEC to provide trophies and cash prizes for podium finishers
All |  | COORDINATION | DJ/Entertainment | Host Gym | Host Gym to provide a live MC for the event, all MCs must receive prior approval from CEC; Host Gym to provide sound system and microphones to extent applicable. Host Gym may provide DJ and other entertainment during the event, subject to approval of CEC; Host Gym may coordinate and after party for the Event
All | 6 hours a.e | MEDIA | TVs | CEC | TV News edits and dope sheets to be provided via an ftp server for TV stations to download (if applicable) | -
All | during event | WEBCAST | Footage | CEC | CEC is responsible for all aspects of webcasting | -
All | 1 month a.e | MEDIA | Press clippings | CEC | CEC will provide press clippings after each event. Event Organizer assistance is requested for National Press clippings | -
All | 2 months a.e | ADMINISTRATION | Event Reporting | CEC | CEC will provide report on the competition organization to the Host Gym and offer to the Host Gym to report on CEC Services | -
All | Upon request | MEDIA | Movies copy | Host Gym | Copies of Semi-finals and finals can be provided to CEC by copying overnight if windows based external hard drive is provided. The main output will be available as MP4 and ISOCAMS will be in either MOV or the raw format from the camera | -
Note on C1: jm: PUT DIFFERENT COLOR